## Sheet1
S I N G A P O R E
|  | TRANSMITTAL LIST | [7 empty] | 1
|  | TO : | SEE DISTRIBUTION LIST BELOW |  |  |  |  | DATE : | 2015-08-26
|  | ATTN : | - |  |  |  |  | REF NO : | P5441
|  | PROJECT : | PARAMOUNT COMMERCIAL MIXED USE DEVELOPMENT @ BATU KAWAN, PENANG, MALAYSIA
S/N | DRAWING NO | DRAWING TITLE |  | DATE |  | 18 | 26
|  |  |  | MONTH |  | 8 | 8
|  |  |  | YEAR |  | 15 | 15
|  |  |  | SCALE | SIZE | REVISION
1 | - | Data Table |  | - | A4 | X | X
2 | CPG/P5441/A100 | Site Plan - Ground Floor Plan |  | 1:1000 | A2 | X | X
3 | CPG/P5441/A101 | Site Plan - Roof Plan |  | 1:1000 | A2 | X | X
4 | CPG/P5441/A102 | Site Plan - Plot Divison |  | 1:1000 | A2 | X | X
5 | CPG/P5441/A200 | Plot 01 - Commercial Retail - Basement, Ground & 1st Floor Plan |  | 1:1000 | A2 | X | X
6 | CPG/P5441/A201 | Plot 01 - Commercial Retail - 2nd to 4th Floor Plan |  | 1:1000 | A2 | X | X
7 | CPG/P5441/A202 | Plot 01 - Studio Apartments & Hotel - 5th to 18th Floor Plan |  | 1:1000 | A2 | X | X
8 | CPG/P5441/A203 | Plot 01 - Studio Apartments & Hotel - Roof Plan |  | 1:1000 | A2 | X | X
9 | CPG/P54411/A250 | Plot 02 - Basement Floor Plan |  | 1:500 | A3 | X | X
10 | CPG/P54411/A251 | Plot 02 - Ground Floor Plan |  | 1:500 | A3 | X | X
11 | CPG/P54411/A252 | Plot 02 - 1st to 3rd Floor Plan |  | 1:500 | A3 | X | X
12 | CPG/P54411/A253 | Plot 02 - 4th Floor Plan |  | 1:500 | A3 | X | X
13 | CPG/P54411/A254 | Plot 02 - Podium Floor Plan |  | 1:500 | A3 | X | X
14 | CPG/P54411/A255 | Plot 02 - 6th to 12th Floor Plan / 15th to 31st Floor Plan |  | 1:500 | A3 | X | X
15 | CPG/P54411/A256 | Plot 02 - 13th Floor Plan |  | 1:500 | A3 | X | X
16 | CPG/P54411/A257 | Plot 02 - 14th Floor Plan |  | 1:500 | A3 | X | X
17 | CPG/P54411/A258 | Plot 02 - Roof Plan |  | 1:500 | A3 | X | X
18 | CPG/P5441/A300 | Plot 01 - Studio Apartment - Typical Floor Plan |  | 1:200 | A3 | X | X
19 | CPG/P5441/A301 | Plot 01 - Studio Apartment - Typologies |  | 1:100 | A3 | X | X
20 | CPG/P5441/A302 | Plot 01 - Hotel - Typical Floor Plan |  | 1:200 | A3 | X | X
21 | CPG/P5441/A303 | Plot 02 - Service Apartment - Typical Floor Plan |  | 1:200 | A3 | X | X
22 | CPG/P5441/A304 | Plot 02 - Service Apartment - Typologies |  | 1:200 | A3 | X | X
23 | CPG/P5441/A305 | Plot 02 - Service Apartment - Podium Facilities Floor Plan |  | 1:200 | A3 | X | X
24 | CPG/P5441/A306 | Plot 02 - Service Apartment - 13th Floor Plan |  | 1:200 | A3 | X | X
25 | CPG/P5441/A307 | Plot 02 - Service Apartment - 14th Floor Plan |  | 1:200 | A3 | X | X
26 | CPG/P5441/A308 | Plot 02 - Service Apartment - Roof Plan
27 | CPG/P5441/A400 | Section A-A' |  | 1:500 | A2 | X | X
28 | CPG/P5441/A401 | Section B-B' |  | 1:1000 | A2 | X | X
29 | CPG/P5441/A402 | Section C-C' |  | 1:500 | A2 | X | X
30 | CPG/P5441/A500 | Elevation 01 |  | 1:500 | A2 | X | X
31 | CPG/P5441/A501 | Elevation 02 |  | 1:1000 | A2 | X | X
|  | DISTRIBUTION LIST |  |  |  | COPIES
| Client | Paramount Property (PW) Sdn Bhd |  |  |  | x | x
| Structural Engineer | Perunding Kelana Civil & Structural Engineer Sdn Bhd |  |  |  | x | x
| M& E Engineer | Perunding P.L.A. Group Consulting Mechanical & Electrical Engineer Sdn Bhd |  |  |  | x | x
| Quantity Surveyor | Unitech QS Consultancy Sdn Bhd |  |  |  | x | x
| Local Architect | BH Yew Architects |  |  |  | x | x
| Planner | Green Acres Studio Sdn Bhd |  |  |  | x | x
| Traffic Consultant | Perunding Trafik Klasik Sdn Bhd |  |  |  |  | x
| Landscape Architect | Landart Design Sdn Bhd |  |  |  |  | x
Others
| For Construction | For Commission / Approval |  |  |  | Yours faithfully
| For Information | For Signature & Return
| For Tender | For Co - ordination
| As Build | Charge
As Requested
Please acknowledge receipt of the above signing and returning the duplicate copy of this drawing masterlist. Thank You.
Date Recevied | [5 empty] | Received By

## Sheet2
S I N G A P O R E
|  | TRANSMITTAL LIST | [7 empty] | Page | 2
|  | TO : | REFER TO DISTRIBUTION LIST BELOW |  |  |  | DATE : | 2010-10-15
|  | ATTN : | - |  |  |  | REF NO : | RS36
|  | PROJECT : | PROPOSED ADDITIONS & ALTERATIONS TO EXISTING CONSERVATION 1-STOREY DWELLING HOUSE AND EXTENSION OF A 2-STOREY DWELLING BUNGALOW WITH BASEMENT, ATTIC AND SWIMMING POOL ON LOT 3359X MK02 AT 26A SWETTENHAM ROAD, SINGAPORE (TANGLIN PLANNING AREA)
S/N | DRAWING NO | DRAWING TITLE |  | DATE | 15
|  |  |  | MONTH | OCT
|  |  |  | YEAR | 10
|  |  |  | SCALE | REVISION
1 | 2BA/RS36/A350 | Enlarged Main Entry Detail- Plan & Elevation 1 |  | 1:40 | x
2 | 2BA/RS36/A351 | Enlarged Main Entry Detail- Elevation 2 and Section A-A |  | 1:40 | x
3 | 2BA/RS36/A355 | Enlarged HS Detail- Plan and Sections A-A & B-B |  | 1:40 | x
4 | 2BA/RS36/A360 | Enlarged Gym/G-Store/Main DB Detail- Plan |  | 1:40 | x
5 | 2BA/RS36/A361 | Enlarged Gym/G-Store/Main DB Detail- Sections A-A & B-B |  | 1:40 | x
6 | 2BA/RS36/A380 | Enlarged Porch Entry @ C Detail- Plan & Roof Plan |  | 1:40 | x
7 | 2BA/RS36/A381 | Enlarged Porch Entry @ C Detail- Sections A-A and B-B |  | 1:40 | x
8 | 2BA/RS36/A385 | Enlarged Wine Cellar @ C Detail- Plan |  | 1:40 | x
9 | 2BA/RS36/A386 | Enlarged Wine Cellar @ C Detail- Sections A-A & B-B |  | 1:40 | x
11 | 2BA/RS36/A400 | Enlarged Stair-1 Detail- Plan and Elevation 1 |  | 1:40 | x
12 | 2BA/RS36/A401 | Enlarged Stair-1 Detail- Section A-A and Details 1 & 2 |  | 1:40, 1:5 | x
13 | 2BA/RS36/A402 | Enlarged Stair-2 Detail- Plan (Basement and 1st) |  | 1:40 | x
14 | 2BA/RS36/A403 | Enlarged Stair-2 Detail- Plan (2nd and Attic) |  | 1:40 | x
15 | 2BA/RS36/A404 | Enlarged Stair-2 Detail- Elevation 1 & Section A-A |  | 1:40 | x
16 | 2BA/RS36/A405 | Enlarged Stair-2 Detail- Sections B-B and C-C |  | 1:40 | x
17 | 2BA/RS36/A406 | Enlarged Stair-2 Detail- Details 1, 2 and 3 |  | 1:25, 1:5 | x
18 | 2BA/RS36/A407 | Enlarged Stair-3 Detail- Plan and Elevation 1 |  | 1:40 | x
19 | 2BA/RS36/A408 | Enlarged Stair-3 Detail- Section A-A & Details 1 and 2 |  | 1:40, 1:5 | x
20 | 2BA/RS36/A409 | Enlarged Stair-4 Detail- Plan & Elevation 1 |  | 1:40 | x
21 | 2BA/RS36/A410 | Enlarged Stair-4 Detail- Section A-A & Details 1 |  | 1:40, 1:5 | x
22 | 2BA/RS36/A411 | Enlarged Stair-4 Detail- Axonometric 1 |  | NTS | x
23 | 2BA/RS36/A420 | Enlarged Ramp Detail- Plan |  | 1:75, 1:10 | x
24 | 2BA/RS36/A421 | Enlarged Ramp Detail- Sections A-A and B-B |  | 1:40 | x
25 | 2BA/RS36/A500 | Reflected Ceiling Plan Lighting Layout- Basement |  | 1:100 | x
26 | 2BA/RS36/A501 | Reflected Ceiling Plan Finishes & Level- Basement |  | 1:100 | x
27 | 2BA/RS36/A502 | Reflected Ceiling Plan Lighting Layout- 1st Storey |  | 1:100 | x
28 | 2BA/RS36/A503 | Reflected Ceiling Plan Finishes & Level- 1st Storey |  | 1:100 | x
29 | 2BA/RS36/A504 | Reflected Ceiling Plan Lighting Layout- 2nd Storey |  | 1:100 | x
30 | 2BA/RS36/A505 | Reflected Ceiling Plan Finishes & Level- 2nd Storey |  | 1:100 | x
31 | 2BA/RS36/A506 | Reflected Ceiling Plan Lighting Layout- Attic |  | 1:100 | x
32 | 2BA/RS36/A507 | Reflected Ceiling Plan Finishes & Level- Attic |  | 1:100 | x
33 | 2BA/RS36/A600 | Door and Window Schedule Key Plan- Basement |  | 1:150 | x
34 | 2BA/RS36/A601 | Door and Window Schedule Key Plan- 1st Storey |  | 1:150 | x
35 | 2BA/RS36/A602 | Door and Window Schedule Key Plan- 2nd Storey |  | 1:150 | x
36 | 2BA/RS36/A603 | Door and Window Schedule Key Plan- Attic |  | 1:150 | x
37 | 2BA/RS36/A610 | Door Schedule 1- Timber Doors |  | 1:50 | x
38 | 2BA/RS36/A611 | Door Schedule 2- Aluminum Frame Glass Doors |  | 1:50 | x
39 | 2BA/RS36/A612 | Door Schedule 3- Aluminum Frame Glass Doors |  | 1:50 | x
40 | 2BA/RS36/A613 | Door Schedule 4- Aluminum Frameless Glass Doors |  | 1:50 | x
41 | 2BA/RS36/A614 | Door Schedule 4- PVC, SS, Metal Grill, Hybrid Doors |  | 1:50 | x
42 | 2BA/RS36/A620 | Door Details 1- Timber Details 1, 2 & 3 |  | 1:5 | x
43 | 2BA/RS36/A621 | Door Details 1- Aluminum Details 1 & 2 |  | 1:5 | x
44 | 2BA/RS36/A630 | Window Schedule 1- Aluminum Frame Glass Windows |  | 1:50 | x
45 | 2BA/RS36/A631 | Window Schedule 2- Aluminum Frame Glass Windows |  | 1:50 | x
46 | 2BA/RS36/A632 | Window Schedule 3- Aluminum Frame Glass Windows |  | 1:50 | x
47 | 2BA/RS36/A640 | Window Details 1- Aluminum Frame Details 1 & 2 |  | 1:5 | x
48 | 2BA/RS36/A641 | Window Details 2- Aluminum Frameless Details 1 & 2 |  | 1:5 | x
49 | 2BA/RS36/A650 | Specialized Door System @Living- Plan (by Dorma) |  | 1:10 | x
50 | 2BA/RS36/A651 | Specialized Door System @Living- Elevation & Detail (by Dorma) |  | 1:10, 1:5 | x
51 | 2BA/RS36/A650 | Door and Window Schedule Key Plan @ C- 1st Storey |  | 1:150 | x
52 | 2BA/RS36/A660 | Door Schedule 1- Timber Doors |  | 1:50 | x
53 | 2BA/RS36/A661 | Door Schedule 2- Aluminium Frame/Frameless Glass Doors |  | 1:50 | x
54 | 2BA/RS36/A670 | Window Schedule 1- Timber Windows |  | 1:50 | x
55 | 2BA/RS36/A671 | Window Schedule 2- Frameless Glass Windows |  | 1:50 | x
|  | DISTRIBUTION LIST |  |  | COPIES
| Client | Mr Thinagaran & Ms Loi Ying Ju |  |  | x
| Structural Engineer | BC Leong and Associates |  |  | x
| M& E Engineer | AE&T Consultants |  |  | x
| Quantity Surveyor | PQS Consultants |  |  | x
| Landscape Architect | -
| Contractor | -
| Others | Tenderers |  |  | x
| For Construction | For Commission / Approval |  |  | Yours faithfully
| For Information | For Signature & Return
| For Tender | For Co - ordination
| As Build | Charge
| As Requested |  |  |  | 2B ARCHITECTS
Please acknowledge receipt of the above signing and returning the duplicate copy of this drawing masterlist. Thank You.
Date Recevied |  |  |  |  | Received By
|  | Media | A3 A2 | A1 |  | Diskette |  |  | Email | Others

## Sheet3
S I N G A P O R E
|  | TRANSMITTAL LIST | [7 empty] | Page | 3
|  | TO : | REFER TO DISTRIBUTION LIST BELOW |  |  |  | DATE : | 2010-10-15
|  | ATTN : | - |  |  |  | REF NO : | RS36
|  | PROJECT : | PROPOSED ADDITIONS & ALTERATIONS TO EXISTING CONSERVATION 1-STOREY DWELLING HOUSE AND EXTENSION OF A 2-STOREY DWELLING BUNGALOW WITH BASEMENT, ATTIC AND SWIMMING POOL ON LOT 3359X MK02 AT 26A SWETTENHAM ROAD, SINGAPORE (TANGLIN PLANNING AREA)
S/N | DRAWING NO | DRAWING TITLE |  | DATE | 15
|  |  |  | MONTH | OCT
|  |  |  | YEAR | 10
|  |  |  | SCALE | REVISION
1 | 2BA/RS36/A700 | Enlarged Gate/Front Boundary Wall- Plan and Elevation |  | 1:75 | x
2 | 2BA/RS36/A701 | Enlarged Main Gate |  | 1:20, 1:5 | x
- Plan, Elevation, Section A-A, Details 1, 2 and 3
3 | 2BA/RS36/A702 | Enlarged Water Feature- Plan & Elevation 1 & Section A-A |  | 1:20 | x
4 | 2BA/RS36/A703 | Enlarged WMeter, Electr/Telecom/SCV Riser, Bin & Mail |  | 1:20 | x
- Elevations 1 and 2 & Section A-A and B-B
5 | 2BA/RS36/A704 | Enlarged Pedestrian Gate- Plan, Elev, Section A-A & Detail 1 |  | 1:20 | x
6 | 2BA/RS36/A705 | Enlarged Steel Fence- Plan, Elevation, Section A-A & Detail1 |  | 1:20, 1:5 | x
7 | 2BA/RS36/A708 | Enlarged Ramp- Plan, Section A-A & Detail 1 |  | 1:20, 1:5 | x
8 | 2BA/RS36/A709 | Enlarged Stone Grating Drain Detail- Typical Details |  | 1:10, 1:5 | x
9 | 2BA/RS36/A710 | Enlarged Car Porch Detail- Roof Plan |  | 1:40 | x
10 | 2BA/RS36/A711 | Enlarged Car Porch Detail- Elevations 1 and 2 |  | 1:40 | x
11 | 2BA/RS36/A712 | Enlarged Car Porch Detail- Section A-A & Section B-B |  | 1:40 | x
12 | 2BA/RS36/A713 | Enlarged Car Porch Detail- Details 1, 2 and 3 |  | 1:10 | x
13 | 2BA/RS36/A714 | Enlarged Car Porch Detail- Axonometric |  | 1:40 | x
14 | 2BA/RS36/A720 | Enlarged Sunken Court 1- Plan |  | 1:50 | x
15 | 2BA/RS36/A721 | Enlarged Sunken Court 1- Elevations 1, 2, 3 and 4 |  | 1:50 | x
16 | 2BA/RS36/A722 | Enlarged Sunken Court 1- Section A-A & Detail 1 |  | 1:50. 1:10 | x
17 | 2BA/RS36/A725 | Enlarged Sunken Court 2- Plan |  | 1:50 | x
18 | 2BA/RS36/A726 | Enlarged Sunken Court 2- Elevations 1, 2 and 3 & Section A-A |  | 1:50 | x
19 | 2BA/RS36/A729 | Enlarged Sunken Court 3- Plan & Section A-A |  | 1:50 | x
20 | 2BA/RS36/A730 | Enlarged Swimming Pool/M&E Rooms- Plan |  | 1:40 | x
21 | 2BA/RS36/A731 | Enlarged Swimming Pool/M&E Rooms- Sections A-A & B-B |  | 1:40 | x
22 | 2BA/RS36/A732 | Enlarged Swimming Pool/M&E Rooms- Section C-C (entry) |  | 1:40 | x
23 | 2BA/RS36/A733 | Enlarged Swimming Pool/M&E Rooms- Details 1, 2 and 3 |  | 1:10 | x
24 | 2BA/RS36/A734 | Enlarged Pool Infinity Edge- Plan, Elevation, Section A-A |  | 1:40 | x
25 | 2BA/RS36/A735 | Enlarged Swimming Pool Deck- Plan |  | 1:40 | x
26 | 2BA/RS36/A740 | Enlarged Pool Deck- Plan |  | 1:60 | x
27 | 2BA/RS36/A741 | Enlarged Pool Deck- Section A-A and Details 1 and 2 |  | 1:60, varies | x
28 | 2BA/RS36/A750 | Enlarged Green Inclinator- Plan & Elevation |  | 1:40 | x
29 | 2BA/RS36/A751 | Enlarged Green Inclinator- Section A-A & Details 1, 2 and 3 |  | 1:40. 1:10 | x
30 | 2BA/RS36/A760 | Enlarged Patio @ C- Plan & Roof Plan |  | 1:40 | x
31 | 2BA/RS36/A761 | Enlarged Patio @ C- Sections A-A and B-B |  | 1:40 | x
32 | 2BA/RS36/A762 | Enlarged Patio @ C- Details 1 and 2 & Axonometric |  | 1:10, NTS | x
33 | 2BA/RS36/A770 | Enlarged Serpentine Green Wall- Plan |  | 1:40 | x
34 | 2BA/RS36/A771 | Enlarged Serpentine Green Wall- Elevation 1 & Section A-A |  | 1:40 | x
35 | 2BA/RS36/A780 | Enlarged Green Horizontal Trellis- Plan, Section A-A |  | 1:40 | x
36 | 2BA/RS36/A781 | Enlarged Green Horizontal Trellis- Details 1 and 2 |  | 1;10 | x
37 | 2BA/RS36/A790 | Green Roof- Plan & Section A-A |  | 1:40 | x
38 | 2BA/RS36/A791 | Green Roof- Details 1 & 2 |  | 1:10 | x
|  | DISTRIBUTION LIST |  |  | COPIES
| Client | Mr See Kee Onn & Ms Lock Yin Mei |  |  | x
| Structural Engineer | BC Leong and Associates |  |  | x
| M& E Engineer | AE&T Consultants |  |  | x
| Quantity Surveyor | PQS Consultants |  |  | x
| Landscape Architect | -
| Contractor | -
| Others | Tenderers |  |  | x
| For Construction | For Commission / Approval |  |  | Yours faithfully
| For Information | For Signature & Return
| For Tender | For Co-ordination
| As Build | Charge
| As Requested |  |  |  | 2B ARCHITECTS
Please acknowledge receipt of the above signing and returning the duplicate copy of this drawing masterlist. Thank You.
Date Recevied |  |  |  |  | Received By
|  | Media | A3 A2 | A1 |  | Diskette |  |  | Email | Others

## Sheet4
S I N G A P O R E
|  | TRANSMITTAL LIST | [7 empty] | Page | 4
|  | TO : | REFER TO DISTRIBUTION LIST |  |  |  | DATE : | 2010-10-15
|  | ATTN : | - |  |  |  | REF NO : | RS36
|  | PROJECT : | PROPOSED ADDITIONS & ALTERATIONS TO EXISTING CONSERVATION 1-STOREY DWELLING HOUSE AND EXTENSION OF A 2-STOREY DWELLING BUNGALOW WITH BASEMENT, ATTIC AND SWIMMING POOL ON LOT 3359X MK02 AT 26A SWETTENHAM ROAD, SINGAPORE (TANGLIN PLANNING AREA)
S/N | DRAWING NO | DRAWING TITLE |  | DATE | 15
|  |  |  | MONTH | OCT
|  |  |  | YEAR | 10
|  |  |  | SCALE | REVISION
1 | 2BA/RS36/A800 | Horizontal Skylight HS1 Detail 1- Plan & Section A-A |  | 1:40 | x
2 | 2BA/RS36/A801 | Horizontal Skylight HS2 Detail 2- Plan & Section A-A |  | 1:40 | x
3 | 2BA/RS36/A802 | Horizontal Skylight HS3 Detail 3- Plan & Section A-A |  | 1:40 | x
4 | 2BA/RS36/A803 | Horizontal Skylight Typical Detail 4- Details 1 and 2 |  | 1:10, 1:5 | x
5 | 2BA/RS36/A804 | Corner Angled Skylight CAS1 Detail- Plan, Elev 1 & Sect A-A |  | 1:40, 1:20 | x
6 | 2BA/RS36/A805 | Corner Angled Skylight CAS1 Detail- Axonometric |  | NTS | x
7 | 2BA/RS36/A806 | Roof Skylight RS1 Detail 1- Plan & Section |  | 1:40 | x
8 | 2BA/RS36/A807 | Roof Skylight RS1 Detail 2- Details 1 & 2 |  | 1:10 | x
9 | 2BA/RS36/A808 | Roof Skylight RS1- Axonometric |  | NTS | x
10 | 2BA/RS36/A810 | Proprietary Metal Roof System 1- Plan |  | 1:40 | x
11 | 2BA/RS36/A811 | Proprietary Metal Roof System 2- Details |  | 1:10 | x
12 | 2BA/RS36/A812 | Proprietary Metal Roof System 3- Details |  | 1:10 | x
13 | 2BA/RS36/A820 | Sky Roof Screen SRS Detail 1- Plan & Elevation |  | 1:40 | x
14 | 2BA/RS36/A821 | Sky Roof Screen SRS Detail 2- Section A-A & Details 1 & 2 |  | 1:40, 1:10 | x
15 | 2BA/RS36/A822 | Sky Roof Screen SRS Detail 1- Plan & Elevation |  | 1:40 | x
16 | 2BA/RS36/A823 | Vertical Metal Screen VS1 Detail 1- Plan & Elevation |  | 1:40 | x
17 | 2BA/RS36/A824 | Vertical Metal Screen VS1 Detail 2- Section A-A & Detail 1 |  | 1:40, 1:5 | x
18 | 2BA/RS36/A825 | Vertical Metal Screen VS2 Detail 1- Plan & Elevation |  | 1:40 | x
19 | 2BA/RS36/A826 | Vertical Metal Screen VS2 Detail 2- Section A-A & Detail 1 |  | 1:40, 1:5 | x
20 | 2BA/RS36/A830 | Glass Balustrade Detail- Section A-A & Detail 1 |  | 1:5, 1:1 | x
21 | 2BA/RS36/A850 | External Stone Cladding EC1 Detail 1- Plan |  | 1:40 | x
22 | 2BA/RS36/A851 | External Stone Cladding EC1 Detail 2- Elev 1 & Section A-A |  | 1:40 | x
23 | 2BA/RS36/A852 | External Stone Cladding EC1 Detail 3- Details 1, 2 and 3 |  | 1:5, 1:2 | x
24 | 2BA/RS36/A853 | External Stone Cladding EC2 Detail 4- Plan |  | 1:40 | x
25 | 2BA/RS36/A854 | External Stone Cladding EC2 Detail 2- Elev 1 & Section A-A |  | 1:40 | x
26 | 2BA/RS36/A855 | External Stone Cladding EC2 Detail 3- Details 1, 2 and 3 |  | 1:5, 1:2 | x
27 | 2BA/RS36/A860 | Timber Deck TD1 Detail- Plan & Section A-A |  | 1:60, 1:20 | x
28 | 2BA/RS36/A861 | Timber Deck TD1 Detail- Details 1 and 2 |  | 1:5 | x
29 | 2BA/RS36/A862 | Timber Floor TF1 Detail- Plan & Details 1 and 2 |  | 1:5 | x
30 | 2BA/RS36/A870 | Timber Cladding- Ceiling recessed & Wall recessed |  | 1:10 | x
|  | DISTRIBUTION LIST |  |  | COPIES
| Client | Mr Thinagaran & Ms Loi Ying Ju |  |  | x
| Structural Engineer | BC Leong and Associates |  |  | x
| M& E Engineer | AE&T Consultants |  |  | x
| Quantity Surveyor | PQS Consultants |  |  | x
| Landscape Architect | -
| Contractor | -
| Others | Tenderers |  |  | x
| For Construction | For Commission / Approval |  |  | Yours faithfully
| For Information | For Signature & Return
| For Tender | For Co-ordination
| As Build | Charge
| As Requested |  |  |  | 2B ARCHITECTS
Please acknowledge receipt of the above signing and returning the duplicate copy of this drawing masterlist. Thank You.
Date Recevied |  |  |  |  | Received By
|  | Media | A3 A2 | A1 |  | Diskette |  |  | Email | Others

## Sheet5
S I N G A P O R E
|  | TRANSMITTAL LIST | [7 empty] | Page | 5
|  | TO : | REFER TO DISTRIBUTION LIST |  |  |  | DATE : | 2010-10-15
|  | ATTN : | - |  |  |  | REF NO : | RS36
|  | PROJECT : | PROPOSED ADDITIONS & ALTERATIONS TO EXISTING CONSERVATION 1-STOREY DWELLING HOUSE AND EXTENSION OF A 2-STOREY DWELLING BUNGALOW WITH BASEMENT, ATTIC AND SWIMMING POOL ON LOT 3359X MK02 AT 26A SWETTENHAM ROAD, SINGAPORE (TANGLIN PLANNING AREA)
S/N | DRAWING NO | DRAWING TITLE |  | DATE | 15
|  |  |  | MONTH | OCT
|  |  |  | YEAR | 10
|  |  |  | SCALE | REVISION
1 | 2BA/RS36/A900 | Waterproofing Key Plan- Basement Plan 1 |  | 1:125 | x
2 | 2BA/RS36/A901 | Waterproofing Key Plan- Basement Plan 2 |  | 1:125 | x
3 | 2BA/RS36/A902 | Waterproofing Key Plan- Lower 1st Storey Plan 1 |  | 1:125 | x
4 | 2BA/RS36/A903 | Waterproofing Key Plan- Lower 1st Storey Plan 2 |  | 1:125 | x
5 | 2BA/RS36/A904 | Waterproofing Key Plan- Upper 1st Storey Plan |  | 1:125 | x
6 | 2BA/RS36/A905 | Waterproofing Key Plan- 2nd Storey Plan |  | 1:125 | x
7 | 2BA/RS36/A906 | Waterproofing Key Plan- Roof Plan |  | 1:125 | x
8 | 2BA/RS36/A907 | Detail 1- Insulated RC Flat Roof |  | NTS | x
9 | 2BA/RS36/A908 | Detail 2- RW Outlet @RC FlatRoof Gutter Details 1 & 2 |  | NTS | x
10 | 2BA/RS36/A909 | Detail 3- RC Flat Roof Parapet Details 1 & 2 |  | NTS | x
11 | 2BA/RS36/A910 | Detail 4- Low Plinth Detail & Pipe Penetrationat RC Flat Roof Detail |  | NTS | x
12 | 2BA/RS36/A911 | Detail 5- Wet Area and Shower Area Detail |  | NTS | x
13 | 2BA/RS36/A912 | Detail 6- Outlet Detail at Wet Area |  | NTS | x
14 | 2BA/RS36/A913 | Detail 7- Typ. Pedestal WC Detail |  | NTS | x
15 | 2BA/RS36/A914 | Detail 8- Typ. Pedestal WC Detail & Bathtub Detail |  | NTS | x
16 | 2BA/RS36/A915 | Detail 9- Typ. Threshold Detail (Bedroom/Bath) & |  | NTS | x
Kitchen/Dining Termination Detail
17 | 2BA/RS36/A916 | Detail 10- Balcony & RC Canopy Detail |  | NTS | x
18 | 2BA/RS36/A917 | Detail 11- Basement Wall & Slab Details 1 & 2 |  | NTS | x
19 | 2BA/RS36/A918 | Detail 12- Ground Beam Detail & Typ. Service Duct |  | NTS | x
20 | 2BA/RS36/A919 | Detail 13- Pipe Penetration @ Basement/Ground |  | NTS | x
|  | Slab Detail & WaterCourt Detail |  | NTS | x
21 | 2BA/RS36/A920 | Detail 14- Swimming Pool Detail |  | NTS | x
22 | 2BA/RS36/A921 | Detail 15- RC Water Tank Detail |  | NTS | x
23 | 2BA/RS36/A930 | Typical Timber Floor Details |  | NTS | x
24 | 2BA/RS36/A950 | Proprietary Metal Roof System 1- Details |  | 1:10 | x
25 | 2BA/RS36/A951 | Proprietary Metal Roof System 2- Details |  | 1:10 | x
26 | 2BA/RS36/A952 | Proprietary Metal Roof System 3- Details |  | 1:10 | x
TENDER ADDENDUM
TENDER ADDENDUM NO. 1 (issuance: Nov ?, 2010)
1 | 2BA/RS36/A420 | Handrail Detail - Stair - 1,Ramp |  | 1:10
2 | 2BA/RS36/A746 | Enlarged Swimming Pool/Pavilion - Detail 1, 2 |  | 1:10
3 | 2BA/RS36/A747 | Enlarged Swimming Pool/Pavilion - Detail 1
TENDER ADDENDUM NO. 1 (issuance: Nov ?, 2010)
1 | 2BA/RS36/A101 - TA | Lower 1 st Storey Plan |  | 1:125
2 | 2BA/RS36/A102 - TA | Upper 1 st Storey Plan |  | 1:125
3 | 2BA/RS36/A103 - TA | 2 nd Storey Plan |  | 1:125
4 | 2BA/RS36/A104 - TA | Roof Storey Plan |  | 1:125
|  | DISTRIBUTION LIST |  |  | COPIES
| Client | Mr Thinagaran & Ms Loi Ying Ju |  |  | x
| Structural Engineer | BC Leong and Associates |  |  | x
| M& E Engineer | AE&T Consultants |  |  | x
| Quantity Surveyor | PQS Consultants |  |  | x
| Landscape Architect | -
| Contractor | -
| Others | Tenderers |  |  | x
| For Construction | For Commission / Approval |  |  | Yours faithfully
| For Information | For Signature & Return
| For Tender | For Co-ordination
| As Build | Charge
| As Requested |  |  |  | 2B ARCHITECTS
Please acknowledge receipt of the above signing and returning the duplicate copy of this drawing masterlist. Thank You.
Date Recevied |  |  |  |  | Received By
|  | Media | A3 A2 | A1 |  | Diskette |  |  | Email | Others